## Activities
Area | Status | Item # | Priority | Activity | Responsible
Venue | Not started | 1 |  | Solidify location - 3 months in advance ideally, or at least one month. Will Rent be needed? Where are the funds coming from?
Venue | Not started | 2 |  | Rooms? How many break out rooms will you need. Need 7, need a large room to hold 40 approx.
Venue | Not started | 3 |  | Send information to the Admin Manager regarding how many registered
Venue | Not started | 4 |  | Accessability - ramps, etc. Parking available if not, what is the cost. Must advertise options.
Venue | Not started | 5 |  | Collaboration with other teams and if the venue has any other events held that day
Venue | Not started | 6 |  | Does the location require insurance? TI does provide insurance.
Venue | Not started | 7 |  | Technology support. Projectors, screens, extension cords. Need technology in ALL rooms.
Venue | Not started | 8 |  | Aquire site map from the Venue and provide this on the registration with Admin manager and provide at the registration desk
Venue | Not started | 9 |  | Some venues provide free rent to "not for profit" organizations.
Venue | Not started | 10 |  | Are you able to bring in food? Do you want to provide food? Fee for Registration? To cover snacks and/or lunch
Venue | Not started | 11 |  | What are the clean up requirements? And Set up?
Registration | Not started | 12 |  | Have the Admin manager set up a registration survey - Survey Monkey OR event brite
Registration | Not started | 13 |  | Print the registrations the night before. There are 2 versions. Registration Desk and Per Office for the Breakout sessions.
Registration | Not started | 14 |  | What sign up requirements are needed? COT role, fee, payment options
Registration | Not started | 15 |  | IF you are accepting payment - a float is needed for Cash payment at the door.
Registration | Not started | 16 |  | Prepare Budget as necessary.
Registration | Not started | 17 |  | Ask for volunteers at time of registrations.
Registration | Not started | 17 |  | Ask at time of registrations for dietary concerns as well
Volunteers | Not started | 18 |  | SAA - must know the emergency procedures of the building. Emergency exits, First Aid stations, washrooms, Muster Points. AED available on site. Assign a First Aider.
Volunteers | Not started | 19 |  | Total volunteer required :10 approx. SAAs for each room. Registration Desk, and people to setup and tear down as required.
Volunteers | Not started | 20 |  | 1 SAA per room.
Volunteers | Not started | 21 |  | What are the expectations of each volunteer position? Define a Leader per team. Delegation is key.
Volunteers | Not started | 22 |  | Who is the volunteer coordinator? Delegation is key.
Program | Not started | 23 |  | Define agenda, facilitors, speakers, time slot, breaks, assign rooms based on registration
Program | Not started | 24 |  | Thank you notes to facilitators
Program | Not started | 25 |  | Agenda's approval of the Leadership team
Program | Not started | 26 |  | Prepare the Agenda, key activities - PRINTING (Ideally 2 nights before) and stick to TI approved branding
Program | Not started | 27 |  | Can you print before hand? If yes - DO!
Program | Not started | 28 |  | Always have a plan B for extra facilitators/ positions. Things happen and been prepared is key for success.
Program | Not started | 29 |  | Evaluation Forms. Printing them and provide them at registration/door.
Program | Not started | 29 |  | Evaluations. Gather results after the training and provide the feedback to each speaker/facilitator. Don't share all.
Program | Not started | 30 |  | Check with Leadership Team regarding montary gifts and thank you's
Program | Not started | 30 |  | Prepare a Master Plan of the event, and add task/activities. This list is not exhaustive. It needs more detail to succeed.
Marketing | Not started | 31 |  | Post on Social Media
Marketing | Not started | 32 |  | Customized messages (mail merge) is mass mailouts the best option
Marketing | Not started | 33 | High | Area Directors to provide listing of officers who still require training - contact them directly
Marketing | Not started | 34 |  | Provide a "why" and how they can participate to the success of the event.
Marketing | Not started | 35 |  | Provide reasons as to why this is good to attend. Testimonials
Marketing | Not started | 36 |  | Invitation should be three months, 1 month and then 1 week to the event. Be careful with massive emails and non applicable regions/areas
Marketing | Not started | 37 |  | recommended to have all logistics in place before marketing.
Marketing | Not started | 38 |  | Ensure the Admin Manager has posted the event.
Note on D1: Omar Nef: Click in cell to assign priority to task

## options
Status | Priority
Not Started | High
In Progress | Medium
Completed | Low